## Verification Matrix (VM)
Requirement Type | Performance |  |  |  | Functional |  |  |  | Design |  |  | Interface |  |  |  | Resource |  | Verfication Reference
Requirement Title | Thermal range sweep | Outside Skin Temp | Overall Power Draw | Output Data | Door and Human/Machine | Final Weight | Connectivity | Endurance | Load sizing and Energy | Internal Volume | Safety and Lockouts | HMI (Built in) | HMI (Website) | Door function | Interior Assy. | Thermo-Fluid Safety | Overall Power Draw | This column identifies the specific verfication summary related to the activity on each line. Multiple summaries may apply to a single line item.
Level of Assembly
Structural | [17 empty] | Includes all structural support, fixtures, and attachments of the system.
Frame | [5 empty] | A,T |  | A | A | A,T |  |  |  |  | A,D | D |  | STR-01, STR-02 (frame base dimensions)
Outer Skin |  | T |  |  |  | A,T |  |  |  | D | [5 empty] | D |  | SAF-02 (temperature)
Handles and Contact Points | [7 empty] | A |  | D | [7 empty] | STR-03 (insulation), SAF-02 (temperature)
HMI Cover |  | M |  |  | A | T | [5 empty] | A,T | [5 empty] | Includes attachment and protection.
Door | D | A,M |  |  | T | A,T |  | A |  | A,D | A,T |  |  | T |  |  |  | CON-04 (thermal control prohibition)
Electrical Component | [17 empty] | Includes all physical electrical components that support the operation and functionalities.
High Voltage |  |  | A |  |  |  | A,T | A | A,T | [7 empty] | A,T | System Requirement 2.3 (using standard supplied power)
PCB | D |  | D | A | A |  | T |  |  |  |  | A | [5 empty] | COM-01 (operatable)
HMI interconnect |  |  |  |  | A |  | A,T |  |  |  |  | T | T |  |  |  |  | Interface Requirement 4.1 (HMI control)
Sensors | D | M |  | D |  |  | A |  |  | I | A,T |  |  | D |  |  |  | COM-05 (proper ratings for system operation); includes sufficient room for necessary monitoring/testing components.
Electrical Safety | [6 empty] | D | A |  |  | T,D |  |  |  | D |  |  | COM-02, COM-03, COM-04 (proper rules, equipment, specifications)
Lamps and Outputs | D |  |  |  | T |  | A | [10 empty] | Indicators for operators are tested under all conditions.
Software | [17 empty] | Governs all automatic & manual control of subsystems that support operations.
HMI | D |  |  | T | T |  | A,T |  |  |  |  | T | T |  |  |  |  | Manual device attached to system for external control and monitoring. Some functions can be verified independently from other subsystems.
Website | D |  |  | T |  |  | A | [5 empty] | D |  |  |  |  | Serves for monitoring & ancillary control; verified through testing subsystems.
Controller | D |  | A | T |  |  | A | A,T | D |  |  | D |  | T |  |  |  | CON-1, CON-02, CON-04, CON-05 (control of temperature setpoints and of component when in use)
Thermo-Fluid | [17 empty] | Includes the individual heating and cooling systems and all components that aid in any thermal changes within the chamber.
Assembly (Vacuum Testing) | [5 empty] | A | [9 empty] | A |  | Preliminary testing
Layout and Design | T | [8 empty] | A | T |  |  |  | I | T |  | THE-03, THE-04 (containment); no obstruction of different components to structure or functions.
Power Systems | D |  | T |  |  |  | T | A | A,T | [6 empty] | T | T | STR-04 (component insulation)
Design Safety |  | M | [8 empty] | T,I |  |  |  |  | T |  | SAF-04, THE-03 (safe-touch from the outside), THE-04 (safe-touch from the outside)
Verification Method: A- Analysis D- Demonstration I- Inspection M- Measurement T- Test V- Validation of Records | Notes: 1. YELLOW: T. BLUE: D. RED: A. GREY: M. 2. Thermo-fluid assembly inlcudes the individual heating and cooling component systems. Assembly testing will need to be proceeded by testing the individual temperature control systems. 3. Each "level of assembly" is a subsystem; the "safety" subsystem is intertwined with the others, and doesn't require it's own level.

## VM & I&T-F; Notes
Notes:
I&T
1 | Integration and Test (I&T) flow displays the chronology and sequence of activities as a system is assembled and tested
2 | Components are combined into subassemblies, which combine into the assembly or assemblies, and finally the system is ready to be tested.
3 | You can distinguish between "responsibility" (person), "location" (as it pertains to the subassemblies), and "progress" using borders, shapes, or colors in the diagram.
VM
1 | Color-coded to display as much information as possible with as little wording as possible.
2 | Verification Reference section is for tying the data into specific requirements or reports.

## VM; Example
Requirement Type→ | Performance |  |  | Functional |  |  | Design |  | Interface | Resource |  | Verification Reference
Requirement Title→ | Measure environmental & compost conditions | Connects to system | Meets consistent system power requirements | Indicate threshold reached | Report data to Website | Hold up to 200 kg | Environmentally Friendly | Reliable & Durable | User Friendly | Meets the required budget | Efficient use of materials and resources | This column identifies the specific verification summary related to the activity on each line. Multiple summaries may apply to a single line item.
Level of Assembly
Systems
Arduino (electronics assembly) |  | D | M |  | T |  |  |  | A | V |  | Section 3.3.X Summaries
Sensor Container (housing assembly) | [6 empty] | A | A | DI | DM | A | Section 3.3.1 - See Note 2
Door Mechanism |  | D |  |  |  |  | A | T | DI | V | A
Subsystems | [11 empty] | Section 3.2.X Summaries
Electronics Assembly |  | D | M |  | T |  |  |  | A | V |  | Section 3.2.1 - See Note 3
Components | [11 empty] | Section 3.1.X Summaries
MicroController | MV |  |  | T |  |  |  |  | D | V
HMI | MV |  |  | T |  |  |  |  | D | AV
| M |  |  | VI |  |  |  |  | D | AV
Materials
Refrigerant | M |  |  | VI |  |  |  |  | D | V
Metal Housing | M |  |  | T |  |  |  |  | D | V
| M |  |  | T |  |  |  |  | D | V
Verification Method: | Notes:
A - Analysis | 1. YELLOW indicates tasks to be done. GREEN indicates completed tasks.
D - Demonstration | 2. Summary References: Resolution (3.3.1), Frame Rate (3.3.2), Mechanical I/F (3.3.3), Electrical I/F (3.3.4), Mass (3.3.5), Power (3.3.6).
I - Inspection | 3. Support electronics used with camera assembly.
M - Measurement
T - Test
V - Validation of Records